## Slide 1: BPF quarterly reporting process
Task | Person/s responsible | Timeframes | Resources
Completion of quarterly report template | GOAP staff & BPF Subcontractors | First week of month | https://s.craft.me/CAPXaByCpNC7dO
Relevant GOAP Sec. staff and GOAP Focal Points to provide outcomes-focused summaries into Defra report. GOAP Sec. staff are to provide updates of their own work and Focal Points are to summarise the work of the subcontractors. | GOAP staff & Focal Points | Second week of month | https://s.craft.me/D0JSAkND8HdKZg
Revision of Defra report, including GOAP team response to any question/comments from MEL lead. | MEL Lead/ GOAP staff | Third week of month | 
Revision of Defra report, with specific attention paid to any country, regional or thematic strategic priorities and/or outcomes | Focal Points | Fourth week of month | 
Directors to add any further strategic level contributions, and report feedback | Directors | Fourth week of month | 
Final adjustments made directly into report | MEL Lead | Final week of month | 
Report submitted to Defra via email | MEL Lead | Last day of month | 
Powerpoint summary created to present to Defra, highlighting outcomes, any questions or priorities to highlight. | MEL Lead | 1-2 weeks after reporting submission | 
Directors to review summary | Directors | 1-2 weeks after reporting submission | 
Meeting with Defra | Directors/ MEL Lead | 2-4 weeks after reporting submission | 

## Slide 2: BPF quarterly reporting process
Task | Person/s responsible | Timeframes | Resources
Quarterly reports analysed for output level data to be extracted and put into NIRAS reporting portal | MEL Lead | Quarterly | NIRAS MEL Hub: https://niras.sharepoint.com/sites/CVPT017397EX2/ Access may need to be requested from NIRAS.
Quarterly reports analysed and intermediate outcome and outcome activities identified and drafted into an 'outcomes harvesting' spreadsheet | MEL Lead | Quarterly | 
'Outcomes harvesting' discussion with the GOAP Team to identify any missing outcomes | Directors/ MEL Lead/ GOAP staff | Quarterly | 
Intermediate outcomes (IO) put into NIRAS tracker Outcomes (O) summary written into NIRAS reporting template | MEL Lead | Quarterly | 
Meeting with NIRAS team to discuss IO and O input (bi-annual only) | MEL Lead/Directors | Quarterly | 
Final revision of IO Tracker and O summaries | Directors | Bi-annual | 
Submission of all IO and O documents through NIRAS reporting portal (bi-annual only) | MEL Lead | Bi-annual | 

## Slide 3: BPF reporting schedule March 2025
Task | Person/s responsible | Due date
‘Activity and Outcomes Reporting template’ quarterly report template due | GOAP Sec. & Subcontractors | 7 March 2025
Qualitative summaries input into the Defra reporting template (in Craft) due | GOAP Sec. & Focal Points | 14 March 2025
Revision of Defra report, including GOAP team response to any question/comments from MEL lead. | MEL Lead | 21 March 2025
Directors to add any further strategic level contributions, and report feedback | Directors | 26 March 2025
Final adjustments made | MEL Lead | 28 March 2025
Report submitted | MEL Lead | 31 March 2025

## Slide 4: BPF reporting schedule – Outcomes reporting March 2025
Task | Person/s responsible | Due date
Quarterly reports analysed for output level data to be extracted and put into NIRAS reporting portal | MEL Lead | April 2025
Quarterly reports analysed, and intermediate outcome and outcome level activities identified and drafted into an 'outcomes harvesting' spreadsheet | MEL Lead | April 2025
'Outcomes harvesting' discussion with the GOAP Team to identify any missing outcomes | MEL Lead / Directors / GOAP Team | April 2025
Intermediate outcomes (IO) put into NIRAS tracker Outcomes (O) summary written into NIRAS reporting template | MEL Lead | Mid May 2025
Meeting with NIRAS team to discuss IO and O input (bi-annual only) | MEL Lead/Directors | TBC - End of May 2025
Final revision of IO Tracker and O summaries | Directors | Early June 2025
Submit all IO and O documents through NIRAS reporting portal (bi-annual only) | MEL Lead | Mid June 2025

## Slide 5: BPF reporting schedule June 2025
Task | Person/s responsible | Due date
‘Activity and Outcomes Reporting template’ quarterly report template due | GOAP Sec. & Subcontractors | 6 June 2025
Qualitative summaries input into the Defra reporting template (in Craft) due | GOAP Sec. & Focal Points | 13 June 2025
Revision of Defra report, including GOAP team response to any question/comments from MEL lead. | MEL Lead | 20 June 2025
Directors to add any further strategic level contributions, and report feedback | Directors | 25 June 2025
Final adjustments made | MEL Lead | 27 June 2025
Report submitted | MEL Lead | 30 June 2025

## Slide 6: BPF reporting schedule September 2025
Task | Person/s responsible | Due date
‘Activity and Outcomes Reporting template’ quarterly report template due | GOAP Sec. & Subcontractors | 5 September 2025
Qualitative summaries input into the Defra reporting template (in Craft) due | GOAP Sec. & Focal Points | 12 September 2025
Revision of Defra report, including GOAP team response to any question/comments from MEL lead. | MEL Lead | 19 September 2025
Directors to add any further strategic level contributions, and report feedback | Directors | 26 September 2025
Final adjustments made | MEL Lead | 29 September 2025
Report submitted | MEL Lead | 30 September 2025

## Slide 7: BPF reporting schedule December 2025
Task | Person/s responsible | Due date
‘Activity and Outcomes Reporting template’ quarterly report template due | GOAP Sec. & Subcontractors | 5 December 2025
Qualitative summaries input into the Defra reporting template (in Craft) due | GOAP Sec. & Focal Points | 12 December 2025
Revision of Defra report, including GOAP team response to any question/comments from MEL lead. | MEL Lead | 18 December 2025
Directors to add any further strategic level contributions, and report feedback | Directors | 22 December 2025
Final adjustments made | MEL Lead | 23 December 2025
Report submitted | MEL Lead | 23 December 2025

## Slide 8: BPF reporting schedule January 2026
Task | Person/s responsible | Due date
‘Activity and Outcomes Reporting template’ quarterly report template due | GOAP Sec. & Subcontractors | 5 September 2025
Qualitative summaries input into the Defra reporting template (in Craft) due | GOAP Sec. & Focal Points | 12 September 2025
Revision of Defra report, including GOAP team response to any question/comments from MEL lead. | MEL Lead | 19 September 2025
Directors to add any further strategic level contributions, and report feedback | Directors | 26 March 2025
Final adjustments made | MEL Lead | 28 March 2025
Report submitted | MEL Lead | 31 March 2025

## Slide 9: Why ocean accounts matter
Changes in ocean wealth, including produced assets (e.g., ports) and non-produced assets (e.g., mangroves, coral reefs).
Ocean-related income and welfare (e.g., income from fisheries for local communities).
Ocean-based economic production (e.g., GDP from ocean-related sectors).
1
2
3
Ocean accounts provide a common information infrastructure for ocean policy development, reporting and decision making; and enable countries to monitor three critical trends:

## Slide 10
10
10